## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Project is in line with the schedule and is progressing nicely. No upcoming issues or risks at this point in time. | 
Status as of | 10-April-2019
Business Lead | Jim Worth
Project Manager | Shay Walker
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/20 | 
Design |  | 100% | 2/20 | 
Coding |  | 85% | 3/29 | 4/24
Testing |  | 35% | 4/17 | 4/24
Training Plan Development |  | 50% | 3/27 | 4/17
Deployment |  | 0% | 5/1 | 5/1
Go Live |  | 0% | 5/1 | 5/8
Hyper Care |  | 0% | 5/8 | 5/8
# | Key Accomplishments (Current Period)
1 | Php functionality is moving forward
2 | Profile Functionality is complete
3 | User Manual is developed and complete
4 | Worked further on the Search Functionality and Help Desk (Ahead of Schedule)
# | Upcoming Activities (Next Period through (04/17/2019)
1 | Finished constructing the Database
2 | Documentation & Training Plan Development
3 | Connection of Pages Finalized to Begin Testing
4 | Help Desk, Search Bar, & Edit Profile Pages PHP Functionality
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
N/A |  |  |  |  |  |  | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
N/A |  |  |  |  |  |  | 
CairnConnect