## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Behind due to Spring Break and Midterms (Lost about 10 days time) Database Administration issues (Access and Editing Privileges were denied) New Project Plan will need to be assessed | 
Status as of | 20-March-2019
Business Lead | Jim Worth
Project Manager | Shay Walker
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/20 | 
Design |  | 100% | 2/20 | 
Coding |  | 50% | 3/39 | 4/3
Testing |  | 0% | 4/17 | 4/24
Training Plan Development |  | 0% | 3/27 | 4/17
Deployment |  | 0% | 5/1 | 5/1
Go Live |  | 0% | 5/1 | 5/8
Hyper Care |  | 0% | 5/8 | 5/8
# | Key Accomplishments (Current Period)
1 | Initial Database Logic for the Registration Page & to populate Majors from the Database
2 | Finished Front end for Help Desk, News & Search Results Pages
3 | Navigation Bar complete with Links
4 | PHP initial code (connecting to the Database)
# | Upcoming Activities (Next Period through (03/27/2019)
1 | Continue constructing the Database
2 | Population of the Database (examples only for testing functionality)
3 | PHP functionality for Login & inserting information in from Registration
4 | PHP functionality for populating Pages with info from the Database
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Testing may be limited due to Delay | Med | Med | The catch up hours should be to offset the Delay and move closer to the intended schedule. | Shay Walker | Med/ High | 4/3
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Project is behind schedule | Med | Med | Work to catch up over weekend hours as needed. As well as a revised Project Plan. | Shay Walker | High | 4/3
CairnConnect