## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
The project is moving along smoothly and at a good pace Many hours of planning and design are coming together to be closer to working on functionality | 
Status as of | 27-Feb-19
Business Lead | Jim Worth
Project Manager | Shay Walker
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 90% | 2/27 | 
Coding |  | 10% | 4/14 | 
SIT - System Test |  | 0% | 4/21 | 
UAT User Acceptance Test |  | 0% | 4/29 | 
Training and Doc |  | 0% | 5/1 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Design of Landing page
2 | Design of Login page, Registration page & Terms and Agreement page
3 | Database Design Development
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Database Design Finalizations
2 | Php Functionality for Login & Registration pages
3 | Design of Personal Profile & News pages
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Some design needs to be changed due to php and database necessities | Low | Med | Research and testing prior to the testing period | Shay Walker | Med | 03/20
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Possible Design changes due to the php functionality | Low | Med | Research and testing will be performed prior to Finalizing designs | Shay Walker | Med | MM/DD
CairnConnect