## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Database work is moving along well leading to readiness for functionality Delays due to Midterms and Break | 
Status as of | 06-March-2019
Business Lead | Jim Worth
Project Manager | Shay Walker
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 95% | 3/13 | 
Coding |  | 25% | 4/17 | 
SIT - System Test |  | 0% | 4/17 | 
UAT User Acceptance Test |  | 0% | 4/17 | 
Training and Doc |  | 0% | 4/17 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/8 | 
# | Key Accomplishments (Current Period)
1 | Initial Database Logic
2 | Design Elemental Changes to Login, Registration, Edit profile, and User Profile pages
3 | Beginning of News Page design
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Building of the Database
2 | Population of the Database (examples only for testing functionality)
3 | Php functionality for populating User Profile
4 | Navbar and Links
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Some design needs to be changed due to php and database necessities | Low | Med | Research and testing prior to the testing period | Shay Walker | Med | 03/20
2 | Project delay (Midterms/Break) | Low | Low | Additional tasks per week/adjust schedule accordingly | Shay Walker | Low | 03/20
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Possible Design changes due to the php functionality | Low | Med | Research and testing will be performed prior to Finalizing designs | Shay Walker | Med | 03/20
2 | Project Delay (Midterms/Break) | Low | Low | Adjust tasks and schedule accordingly | Shay Walker | Low | 03/20
CairnConnect